## Apr_Jul
SCT Cables and Patch Panels |  |  | 2006-07-28
[5 empty] | April |  |  |  | May |  |  |  | June |  |  |  |  | July
|  |  |  | 2006-04-03 | 2006-04-10 | 2006-04-17 | 2006-04-24 | 2006-05-01 | 2006-05-08 | 2006-05-15 | 2006-05-22 | 2006-05-29 | 2006-06-05 | 2006-06-12 | 2006-06-19 | 2006-06-26 | 2006-07-03 | 2006-07-10 | 2006-07-17 | 2006-07-24
Type IV |  | French team |  | 2006-04-17: 63; 2006-04-24: 63; 2006-05-01: 56; 2006-05-08: 63; 2006-05-15: 63; 2006-05-22: 60; 2006-05-29: 72 | 440
Installation |  | Russian team |  | 600 |  | 80 |  | 80 | 80 | 80 | 80 | 100 | 100 | 100 | 90 | 94 | 100 | 100 | 100 | 100 | 1684 | 0
Acceptance |  |  |  | 2 shifts | * | Japan | Japan | * | * | * | * | * | Manchester | *
|  |  |  | * | * | Japan | Japan | * | * | * | * | * | Manchester | *
Test in rack after installation | [6 empty] | * | * | Japan | Lancaster | * | * | Glasgow | * | Ken | Ken | * | * | Ken | Alexandre
[7 empty] | * | * | Japan | Lancaster | * | * | Glasgow | * | Tomas | Kuo-Ming | * | * | Yan | *
Connector in situ by external company - CPE |  |  |  | 2006-05-22: 200 | 1924
Test of cut cables with connector |  |  |  | 2006-04-03: Petr; 2006-04-10: Petr; 2006-04-17: Petr; 2006-05-01: *; 2006-05-08: *
|  |  |  | * | Freiburg | * | * | * | *
Plug-in cables into PS crates + test | [6 empty] | Freiburg |  |  | Petr | Petr | Petr | * | * | * | Petr | Petr | Petr | Petr | Petr
Jan B
|  |  |  | Edward |  |  | Petr | Petr | Petr | Prague | Prague | Freiburg | * | * | * | Jan S | Jan Broz | Jan Broz | Jan Broz | Eva G
|  |  |  | Stefan |  |  | JanB | JanB | JanB | JanB | JanB | JanB | * | * | * | Jano H | Jano H |  |  | Anna M
Type II-III
Installation | [5 empty] | 616 | 262 | 144 | 192 | 252 | 319 | 307 | 319 | 264 | 120 | 127 | 336 | 336 |  |  | 3594 | 494
Preparation |  |  |  | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Kuo-Ming | Tomas | Jessica | * | * | Tomas | Tomas | * | Tomas
Acceptance + organize cables for installation |  |  |  | Martin | Freiburg | * | Geneva | Geneva | Geneva | Geneva | Geneva | Jessica | Jessica | Katharine | * | * | * | * | *
Folding of shield |  |  |  | * | * | * | Geneva | Geneva | Geneva | Geneva | Geneva | Freiburg | Kuo-Ming | * | * | MPI | MPI | * | * | Ken
|  |  |  | * | * | Neil | Glasgow | Japan | Glasgow | Freiburg | * | * |  | * | * | Freiburg | Yan | Yan | * | Yan
|  |  |  | * | * | * | Glasgow | Japan | Glasgow | Freiburg | * | * |  | * | * | Freiburg | Edward | Edward | * | Edward
[7 empty] | Freiburg | Kuo-Ming | Kuo-Ming | Kuo-Ming | Kuo-Ming | * | Manchester | * |  | Freiburg | Ken | Ken | *
[7 empty] | Freiburg | TomB | * | * | * | * | Manchester | * |  | Freiburg | * | * | * | *
Mounting dPPB1 & dPPF1
Barrel: | Squeeze the cables to fit between pin and clamp holder |  |  | Lars | Lars | Lars | * | * | Lars | Lars | Lars
Plug-in to dPPB1, place the clamp, arrange drain wire |  |  |  | Neil | Neil | Neil | Neil | Neil | Neil | Neil | * | * | * | *
Endcap: | Crimping of drain wires, plug in the dPPF1 |  |  | * | * | * | * | * | Jacek | Jacek | Jacek | Jacek | Jacek | Jacek | Jacek | Jacek | Jacek | Jacek
Test cables after installation |  |  |  | Martin | * | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre
[7 empty] | JanB: Janice; JanB: Freiburg | UCL | * | * | Tomas | * | * | Tomas
[7 empty] | JanB: Freiburg |  | Tomas | * | * | Martin | * | *
|  |  |  | * | * | * | * | * | * | Martin | Martin | * | * | Kuo-Ming | Kuo-Ming | * | * | * | *
PP3
Installation (most of the subracks already installed)
Test/Burn-in of units |  |  |  | Scott | Scott | Scott | [8 empty] | Scott | bar: JanB to JanB
Assembly into subracks |  |  |  | Edward +1 shift | Edward | Scott | [8 empty] | * | Scott | bar: JanB to JanB
Installation into racks/rework |  |  |  | Scott | Scott | Scott | * | * | * | MPI | MPI | * | * | Scott | Scott | Scott | Scott | Scott | Scott
Plug-in cables to PP3 |  |  |  |  | 1 shift | * | [6 empty] | * | * | * | * | * | * | * | bar: JanB to JanB
Type IV |  |  | as of March 10, 2100+ cables in US side and 602 cables in USA side already installed - 1522 cables to install since then
Type II-III |  |  | 4088 cables | 400 cables/week
Connector in situ by external company - CPE |  |  | as of March 10 almost all US side connectors built, to be completed before starting in USA side. Also rack 05 to be reworked, possibly by May 15
PP3 |  |  | as of April 20 most of the subracks assembled and installed - see PP3 sheet
done | to be done | part-time
Shits assignments are subject to change depending on people arrival/departure, people's skills, tester performance, cable arrival and change in priorities.
People longterm (currently) |  |  | start | end |  | start | JanB: end
Vlastik Kral |  | Prague | 2006-03-01 | 2006-05-30
Kuo-Ming Lee |  | Academia Sinica | 2006-05-08 | 2006-06-30
Alexandre Nadtochiy |  | Dubna | 2006-04-17 |  |  |  | JanB: 2006-09-24
Scott Moncrieff |  | Melboune | Feb | 2006-04-18 |  | 2006-06-12 | JanB: 2006-07-28
Jessica Metcalfe |  | UC Santa Cruz | 2006-05-29 | 2006-06-12
Ken Fowler |  | UC Santa Cruz | 2006-06-19 |  |  |  | JanB: 2006-08-14
Tomas Slavicek |  | Prague | 2006-06-05 |  |  |  | JanB: 2006-09-01
Petr Kubik |  | Prague | summer 2005 | 2006-06-05 |  | 2006-06-28
Yan Grange |  | Nikhef | 2006-07-03
Edward Gornicki |  | Crakow | 2006-07-03 |  |  |  | JanB: 9 months

## Aug_Nov
SCT Cables and Patch Panels
| 2006-10-15 | [5 empty] | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November
|  |  |  | 2006-07-17 | 2006-07-24 | 2006-07-31 | 2006-08-07 | 2006-08-14 | 2006-08-21 | 2006-08-28 | 2006-09-04 | 2006-09-11 | 2006-09-18 | 2006-09-25 | 2006-10-02 | 2006-10-09 | 2006-10-16 | 2006-10-23 | 2006-10-30 | 2006-11-03 | 2006-11-10 | 2006-11-17 | 2006-10-23 | 2006-10-30
Type II-III | [10 empty] | 247 | 247
Installation | [10 empty] | 147 | 180 | 167
Mounting dPPB1 & dPPF1
Endcap: | Crimping of drain wires, plug in the dPPF1 | [7 empty] | Jacek | Jacek | Jacek | Jacek | Jacek
Test all cables installed in synch with installation | [10 empty] | Alexandre | Alexandre | Thomas
*
Type IV
Installation |  | Russian team
Test in rack after installation |  |  |  | Tomas
Yan
Connector in situ by external company - CPE | [5 empty] | 100 | 100 | 200 | 250 | 250 | 250 | 250 | 250 | 274 |  |  |  |  | 1924
[6 empty] | 0 | 0 | 200 | 200 | 200 | 100 | 100 | 200 | 200 | 200
Test of cut cables after connector | [6 empty] | Tomas | Regina | Regina | Regina | Regina | Regina | Regina | Regina | J Broz | J Broz |  | Edward | 524
[7 empty] | Edward | Ken | * | * | Barbara | Barbara | ….¦Andre | Andre | Andre | Andre | Andre | Andre
[7 empty] | Regina | Andre | Andre | Andre | Andre | Tomas
[6 empty] | Anthony | Anthony | Gabe | Gabe | Gabe
Plug-in cables into PS crates + test |  |  |  | Petr | Petr | Petr | Petr | Petr | Petr |  |  |  | Petr | Petr
|  |  |  | Jan Broz | Jan B | Jan B | [7 empty] | Jan B | Jan B | Jan B |  |  |  |  | Jan B | Jan B | Jan B
[5 empty] | Eva G | Eva G | [7 empty] | Eva G | Eva G | Eva G |  |  |  |  | Eva G | Eva G | Eva G
[5 empty] | Anna M | Anna M | [7 empty] | Anna M | Anna M | Anna M |  |  |  |  | Anna M | Anna M | Anna M
|  |  |  | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre |  |  |  | Jan S | Jan S | [5 empty] | Jan S
|  |  |  | Ken | Ken | Ken | Ken | [5 empty] | Jano H | Jano H | [5 empty] | Jano H
[5 empty] | Andre | Andre | Gabe | [6 empty] | J Broz | [6 empty] | J Broz
[5 empty] | Barbara | Barbara | Barbara | Barbara | Barbara | [5 empty] | Petr | Petr | Petr | Petr | Petr |  | Petr | Petr | Petr | Petr
[5 empty] | Edward | Edward |  | Edward | Edward |  |  |  |  | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre |  | Alexandre | Alexandre | Alexandre | Alexandre
[5 empty] | Tomas | Tomas |  | Tomas | [10 empty] | Andre |  | Andre | Andre | Andre | Andre
[19 empty] | Edward |  | Jacek | Jacek | Jacek | Jacek
[21 empty] | Edward | Edward | Edward | Edward
TEST whole chain | [6 empty] | US side | [5 empty] | Barrel-> | Sector 7 | Sector 9 | Sector 11 | Sector 1 | Sector 3 | Sector 15 | Endcap-> | Sector 7 | Sector 9 | Sector 11
[14 empty] | 336 | 384 | 336 | 384 | 336 | 336
2112
2112
PP3 | Rework | [11 empty] | Sector 7 | Sector 9+11+1+3+15
[11 empty] | Ashley | Ashley | Ashley | Ashley
[11 empty] | Scott | Scott | Scott | Scott
[12 empty] | Barbara | Tomas | Gilbert +Jean
[12 empty] | Thomas | Edward | Stefan
[12 empty] | Regina | Stefan | Edward
[6 empty] | Disconnect PP3 racks |  |  |  | Sector11 | Sector15+11 | Sector1+3+9 | Sector7
[6 empty] | Connect PP3 racks | [6 empty] | Type IV-> | Sector7 | Sector9+11 | Sector1 | Sector 1 | Sector 3 | Sector15
[13 empty] | Type III-> | Sector7 | Sector9+15 | Sector11 | Sector 1 | Sector 3
[10 empty] | Petr | Petr | Petr |  | Jacek | Tony | Jacek | Jacek | Jacek | Jacek
[10 empty] | Tomas | Tomas | Lina |  | * | Ellie |  |  | * | *
[10 empty] | Alexandre |  | Fred |  | Alden | Ingmar | Ingmar |  | *
|  |  | PP3 checks | Scott | Scott |  |  |  |  | Barbara | …¦Stefan | Stefan |  | Tomas | Edward |  |  | * | *
|  |  |  | Anthony | Anthony | [9 empty] | Nobu | Andy E | Freiburg | Joe B. | Bergen* | Bergen*
[15 empty] | Reisaburo | Mike P | Freiburg | Richard S.
done | to be done | part-time | installation of PS | [7 empty] | Edward | Edward |  |  | Gilbert +Jean | Gilbert +Jean | Freiburg | *
Shits assignments are subject to change depending on people arrival/departure, people's skills, tester performance, cable arrival and change in priorities.
People longterm
|  |  | From | UNTIL
Alexandre Nadtochiy |  | Dubna |  | 2006-10-27 | possibly extended
Tomas Slavicek |  | Prague |  | 2006-09-29
Petr Kubik |  | Prague |  | November
Jacek Pieron |  | Cracow | 2006-08-20 | 2006-09-29 | returning 2nd week of October for 4 weeks
Barbara Toczek |  | Cracow | 2006-07-24 | 2006-09-15
Edward Gornicki |  | Cracow |  | 2007-03-01 | 2007
Regina Moles |  | Valencia | 2006-08-07 | 2006-09-29 | half day
Andre Sopczak |  | Uppsala |  | 2006-12-01 | mornings | week of 18 Sep half week after 20 Sep
Ken Fowler |  | UC Santa Cruz |  | 2006-08-14
Gabe Hare |  | UC Santa Cruz | 2006-08-04 | 2006-09-01
Anthony Waugh |  | University of Sydney |  | 2006-08-11 | afternoons
Stefan Koperny |  | Cracow | 2006-09-08 | 2006-09-29
shifts for PP3 and reconnecting
| am |  |  | pm
2006-09-27 | Gilbert+Jean |  |  | Gilbert+Jean
2006-09-28 | Stephen H. |  |  | Stephen H.
Alden
2006-09-29 | Janet C.
2006-10-02
2006-10-03 | Gilbert+Jean |  |  | Gilbert+Jean
Reisaburo
2006-10-04 | Gilbert+Jean |  |  | Gilbert+Jean
Tony
Reisaburo
2006-10-05 |  |  |  | Tony + Ellie
Reisaburo
2006-10-06 | Tony+Ellie

## PP3-rework-current
2006-10-02 |  | Priority for PP3 rework
| Disconnect | Rework | connect typeIV | connect typeIII | test of whole chain
week0 | Y.52-25.X2
Y.53-25.X2
week1 | Y.51-25.X1
4.09 | Y.52-02.X2
| Y.51-02.X2 | Y.51-25.X1
week2 | Y.53-02.X2 | preparation | Y.51-25.X1
11.09 | Y.52-01.X6 | preparation
| Y.43-01.X6 | preparation
| Y.37-01.X6 | preparation
| Y.47-01.X6 | preparation
| Y.52-04.X7 | preparation
| Y.53-04.X7 | preparation
| Y.51-26.X5 | preparation
| Y.53-26.X5 | preparation
week3 | Y.53-23.X8 | preparation
18.09 | Y.52-23.X8 | preparation
| Y.51-23.X8 | preparation
preparation
Y.52-23.X8
Y.51-23.X8
Y.53-23.X8
Y.51-26.X5
Y.53-26.X5
Y.52-25.X2
Y.53-25.X2
week4 |  | Y.52-01.X6 | Y.52-23.X8 | Y.52-23.X8
2006-09-25 |  | Y.43-01.X6 |  |  | Y.52-23.X8
|  | Y.37-01.X6 | Y.51-23.X8
|  | Y.47-01.X6 |  | Y.51-23.X8
|  | Y.52-04.X7 | Y.51-26.X5
Y.53-04.X7
|  | Y.52-02.X2 | Y.53-26.X5 |  | Y.51-23.X8
Y.51-02.X2
Y.53-02.X2
week5 |  |  |  | Y.51-26.X5
2006-10-02 |  |  | Y.52-25.X2 |  | Y.51-26.X5
Y.53-25.X2
Y.53-26.X5
|  |  | Y.53-23.X8 | Y.52-02.X2 | Y.53-26.X5
Y.51-02.X2
Y.53-02.X2
week6 |  |  | Y.52-01.X6 | Y.52-25.X2 | Y.52-25.X2
2006-10-09 |  |  | Y.43-01.X6
|  |  |  | Y.53-25.X2 | Y.53-25.X2
|  |  |  | Y.51-25.X1 | Y.51-25.X1
week7 |  |  | Y.37-01.X6 | Y.52-01.X6 | Y.52-01.X6
2006-10-16 |  |  | Y.47-01.X6 | Y.43-01.X6 | Y.43-01.X6
|  |  |  | Y.37-01.X6 | Y.37-01.X6
|  |  |  | Y.47-01.X6 | Y.47-01.X6
week8 |  |  | Y.52-04.X7 | Y.52-04.X7 | Y.52-04.X7
2006-10-23 |  |  | Y.53-04.X7
|  |  |  | Y.53-04.X7 | Y.53-04.X7
week9 |  |  | Y.52-02.X2 |  | Y.52-02.X2
2006-10-30 |  |  | Y.51-02.X2
|  |  | Y.53-02.X2 |  | Y.51-02.X2
Y.53-02.X2

## PP3-rework-Sep21
2006-09-21 |  | Priority for PP3 rework
| Disconnect | Rework | connect typeIV | connect typeIII | test of whole chain
week0 | Y.52-25.X2
Y.53-25.X2
week1 | Y.51-25.X1
4.09 | Y.52-02.X2
| Y.51-02.X2 | Y.51-25.X1
week2 | Y.53-02.X2 | preparation | Y.51-25.X1
11.09 | Y.52-01.X6 | preparation
| Y.43-01.X6 | preparation
| Y.37-01.X6 | preparation
| Y.47-01.X6 | preparation
| Y.52-04.X7 | preparation
| Y.53-04.X7 | preparation
| Y.51-26.X5 | preparation
| Y.53-26.X5 | preparation
week3 | Y.53-23.X8 | preparation
18.09 | Y.52-23.X8 | preparation
| Y.51-23.X8 | preparation
preparation
Y.52-23.X8
Y.51-23.X8
Y.53-23.X8
week4 |  | Y.51-26.X5 | Y.52-23.X8 | Y.52-23.X8
2006-09-25 |  | Y.53-26.X5 |  |  | Y.52-23.X8
|  | Y.52-25.X2 | Y.51-23.X8
|  | Y.53-25.X2 |  | Y.51-23.X8
|  | Y.52-01.X6 | Y.51-26.X5 |  | Y.51-23.X8
|  | Y.43-01.X6 | Y.53-26.X5
week5 |  | Y.37-01.X6 |  | Y.51-26.X5
2006-10-02 |  | Y.47-01.X6 | Y.52-25.X2 |  | Y.51-26.X5
|  | Y.52-04.X7 | Y.53-25.X2
|  | Y.53-04.X7 |  | Y.53-26.X5
|  | Y.52-02.X2 | Y.53-23.X8 |  | Y.53-26.X5
Y.51-02.X2
Y.53-02.X2
week6 |  |  | Y.52-01.X6 | Y.52-25.X2 | Y.52-25.X2
2006-10-09 |  |  | Y.43-01.X6
|  |  |  | Y.53-25.X2 | Y.53-25.X2
|  |  |  | Y.51-25.X1 | Y.51-25.X1
week7 |  |  | Y.37-01.X6 | Y.52-01.X6 | Y.52-01.X6
2006-10-16 |  |  | Y.47-01.X6 | Y.43-01.X6 | Y.43-01.X6
|  |  |  | Y.37-01.X6 | Y.37-01.X6
|  |  |  | Y.47-01.X6 | Y.47-01.X6
week8 |  |  | Y.52-04.X7 | Y.52-04.X7 | Y.52-04.X7
2006-10-23 |  |  | Y.53-04.X7
|  |  |  | Y.53-04.X7 | Y.53-04.X7
week9 |  |  | Y.52-02.X2 | Y.52-02.X2 | Y.52-02.X2
2006-10-30 |  |  | Y.51-02.X2
|  |  | Y.53-02.X2 | Y.51-02.X2 | Y.51-02.X2
|  |  |  | Y.53-02.X2 | Y.53-02.X2

## PP3-rework
| UX rack | PS racks | Barrel/ Endcap | sector | priority for connector in situ | Connector in situ |  | Connection of type III by Sergei | Priority for PP3 rework | [5 empty] | Priority for PP3 rework
[9 empty] | disconnect | rework | connect type IV | connect type III | 2006-09-01
| Y.51-23.X8 | Y.26-11.A2 | B | 7 | 1 | DONE | Y.51-23.X8 |  | 5 | 5 | 6 | 6 |  | Disconnect | Rework | connect typeIV | connect typeIII | test of whole chain
| Y.52-23.X8 | Y.22-14.A2 | B/E | 7 | 1 | DONE | Y.52-23.X8 |  | 5 | 5 | 6 | 6
| Y.53-23.X8 | Y.27-11.A2 | E | 7 | 4 |  | Y.53-23.X8 |  | 5 | 5 | 5 | 6 | week0 | Y.52-25.X2
| Y.51-26.X5 | Y.23-14.A2 | E | 9 | 4 |  | Y.51-26.X5 | DONE | 4 | 4 | 5 | 4 |  | Y.53-25.X2
USA | Y.51-26.X5 | Y.29-11.A2 | B/E |  | 2 | In progress | [6 empty] | week1 | Y.51-25.X1
| Y.53-26.X5 | Y.29-11.A2 | B/E | 9 |  |  | Y.53-26.X5 | DONE | 4 | 4 | 6 | 4 | 4.09 | Y.52-02.X2
| Y.53-26.X5 | Y.28-11.A2 | B/E |  | 2 | In progress | [7 empty] | Y.51-02.X2 | Y.51-25.X1
| Y.52-25.X2 | Y.25-11.A2 | B | 11 | 1 | DONE | Y.52-25.X2 | DONE | 1 | 1 | 1 | 5 | week2 | Y.53-02.X2 | Y.52-02.X2 | Y.51-25.X1
| Y.52-25.X2 | Y.28-14.A2 | B |  | 2 | In progress | [6 empty] | 11.09 | Y.52-01.X6 | Y.51-02.X2 | Y.52-02.X2
| Y.53-25.X2 | Y.28-14.A2 | B | 9 |  |  | Y.53-25.X2 | DONE | 1 | 1 | 1 | 4 |  | Y.43-01.X6 | Y.53-02.X2 | Y.51-02.X2 | Y.52-02.X2 | Y.52-02.X2
| Y.53-25.X2 | Y.29-14.A2 | B/E |  | 3 | [8 empty] | Y.37-01.X6 | Y.52-01.X6 | Y.53-02.X2 | Y.51-02.X2 | Y.51-02.X2
| Y.51-25.X1 | Y.26-14.A2 | B/E | 11 | 3 | DONE | Y.51-25.X1 |  | 1 | 1 | 1 | 5 | week3 | Y.47-01.X6 | Y.43-01.X6 | Y.52-01.X6 | Y.53-02.X2 | Y.53-02.X2
| Y.51-25.X1 | Y.27-14.A2 | E |  | 4 | [7 empty] | 18.09 | Y.52-04.X7 | Y.37-01.X6 | Y.43-01.X6 | Y.52-01.X6 | Y.52-01.X6
| Y.53-23.X8 | Y.27-14.A2 | E | 7 | [9 empty] | Y.53-04.X7 | Y.47-01.X6 | Y.37-01.X6 | Y.43-01.X6 | Y.43-01.X6
| Y.51-26.X5 | Y.27-14.A2 | E | 9 | [9 empty] | Y.51-26.X5 | Y.52-04.X7 | Y.47-01.X6 | Y.37-01.X6 | Y.37-01.X6
| Y.53-26.X5 | Y.27-14.A2 | E | 9 | [9 empty] | Y.53-26.X5 | Y.53-04.X7 | Y.52-04.X7 | Y.47-01.X6 | Y.47-01.X6
[15 empty] | Y.51-26.X5 | Y.53-04.X7 | Y.52-04.X7 | Y.52-04.X7
+ | priority 4 because bottom crates are shared with sector 9 | [11 empty] | week4 | Y.53-23.X8 | Y.53-26.X5 | Y.51-26.X5 | Y.53-04.X7 | Y.53-04.X7
++ | top 2 crates can be connected later | [11 empty] | 25.09 | Y.52-23.X8 | Y.52-25.X2 | Y.53-26.X5 | Y.51-26.X5 | Y.51-26.X5
+++ | priority 1 for connector in situ because of vicinity to fibres rack | [12 empty] | Y.51-23.X8 | Y.53-25.X2 | Y.52-25.X2 | Y.53-26.X5 | Y.53-26.X5
[15 empty] | Y.53-23.X8 | Y.53-25.X2 | Y.52-25.X2 | Y.52-25.X2
[15 empty] | Y.52-23.X8 | Y.53-23.X8 | Y.53-25.X2 | Y.53-25.X2
[15 empty] | Y.51-23.X8 | Y.52-23.X8 | Y.51-25.X1 | Y.51-25.X1
[13 empty] | week5 |  |  | Y.51-23.X8 | Y.53-23.X8 | Y.53-23.X8
[13 empty] | 2006-10-02 |  |  |  | Y.52-23.X8 | Y.52-23.X8
[17 empty] | Y.51-23.X8 | Y.51-23.X8
| UX rack | PS racks | Barrel/ Endcap | sector | priority for connector in situ | Connector in situ |  | Connection of type III by Sergei
| Y.37-01.X6 | Y.05-14.S2 | B | 1 |  | DONE | Y.37-01.X6 | DONE | 2 | 2 | 3 | 2 |  |  | Priority for PP3 rework
2006-09-16
| Y.43-01.X6 | Y.10-15.S2 | E | 1 |  | DONE | Y.43-01.X6 | DONE | 2 | 2 | 3 | 2 |  | Disconnect | Rework | connect typeIV | connect typeIII | test of whole chain
| Y.43-01.X6 | Y.11-15.S2 | E | 1 |  | DONE |  |  |  |  | 3
| Y.47-01.X6 | Y.11-15.S2 | E | 1 |  |  | Y.47-01.X6 | DONE | 3 | 3 | 3 | 2 | week0 | Y.52-25.X2
US | Y.43-01.X6 | Y.12-15.S2 | B | 1 |  | DONE | [7 empty] | Y.53-25.X2
| Y.47-01.X6 | Y.12-15.S2 | B/E | 1 | [8 empty] | week1 | Y.51-25.X1
| Y.52-01.X6 | Y.23-15.S2 | B | 1 |  | DONE | Y.52-01.X6 | DONE | 3 | 3 | 3 | 2 | 4.09 | Y.52-02.X2
| Y.52-04.X7 | Y.23-15.S2 | B | 3 |  |  | Y.52-04.X7 | DONE | 3 | 3 | 4 | 3 |  | Y.51-02.X2 | Y.51-25.X1
| Y.52-04.X7 | Y.24-15.S2 | B | 3 |  | DONE | [6 empty] | week2 | Y.53-02.X2 | preparation | Y.51-25.X1
| Y.53-04.X7 | Y.25-15.S2 | E | 3 |  | DONE | Y.53-04.X7 | DONE | 3 | 3 | 4 | 3 | 11.09 | Y.52-01.X6 | preparation
| Y.53-02.X2 | Y.26-15.S2 | E | 15 |  | DONE | Y.53-02.X2 |  | 2 | 2 | 2 | 1 |  | Y.43-01.X6 | preparation
| Y.51-02.X2 | Y.27-15.S2 | E | 15 |  | DONE | Y.51-02.X2 |  | 2 | 2 | 2 | 1 |  | Y.37-01.X6 | preparation
| Y.53-04.X7 | Y.27-15.S2 | B/E | 3 | [9 empty] | Y.47-01.X6 | preparation
| Y.51-02.X2 | Y.28-15.S2 | B | 15 |  | DONE | [7 empty] | Y.52-04.X7 | preparation
| Y.52-01.X6 | Y.28-15.S2 | B | 1 | [9 empty] | Y.53-04.X7 | preparation
| Y.52-02.X2 | Y.29-15.S2 | B | 15 |  | DONE | Y.52-02.X2 | DONE | 1 | 1 | 2 | 1 |  | Y.51-26.X5 | preparation
[14 empty] | Y.53-26.X5 | preparation
[13 empty] | week3 | Y.53-23.X8 | preparation
* | priority 1 because top crate(s) belongs to (shared with) sector 1 | [11 empty] | 18.09 | Y.52-23.X8 | preparation
** | only top crate | [12 empty] | Y.51-23.X8 | preparation
Y.52-02.X2
[15 empty] | Y.51-02.X2 |  | Y.52-02.X2
[15 empty] | Y.53-02.X2 |  | Y.51-02.X2
[13 empty] | week4 |  | Y.53-23.X8 |  | Y.53-02.X2
[13 empty] | 2006-09-25 |  | Y.52-23.X8 | Y.53-23.X8
| 9/1/12006 | [13 empty] | Y.51-23.X8 | Y.52-23.X8 | Y.53-23.X8
[15 empty] | Y.51-26.X5 | Y.51-23.X8 | Y.52-23.X8 | Y.52-23.X8
[15 empty] | Y.53-26.X5 |  | Y.51-23.X8 | Y.51-23.X8
Y.52-25.X2
Y.53-25.X2
[13 empty] | week5 |  | Y.52-01.X6 | Y.51-26.X5 | Y.51-26.X5
[13 empty] | 2006-10-02 |  | Y.43-01.X6 | Y.53-26.X5 | Y.53-26.X5 | Y.51-26.X5
[15 empty] | Y.37-01.X6 | Y.52-25.X2 | Y.52-25.X2 | Y.53-26.X5
[15 empty] | Y.47-01.X6 | Y.53-25.X2 | Y.53-25.X2
[15 empty] | Y.52-04.X7 |  | Y.51-25.X1
Y.53-04.X7
[13 empty] | week6 |  |  | Y.52-01.X6 | Y.52-01.X6 | Y.52-25.X2
[13 empty] | 2006-10-09 |  |  | Y.43-01.X6 | Y.43-01.X6 | Y.53-25.X2
[16 empty] | Y.37-01.X6 | Y.37-01.X6 | Y.51-25.X1
[16 empty] | Y.47-01.X6 | Y.47-01.X6
[13 empty] | week7 |  |  | Y.52-04.X7 | Y.52-04.X7 | Y.52-01.X6
[13 empty] | 2006-10-16 |  |  | Y.53-04.X7 | Y.53-04.X7 | Y.43-01.X6
[16 empty] | Y.52-02.X2 |  | Y.37-01.X6
[16 empty] | Y.51-02.X2 |  | Y.47-01.X6
[13 empty] | week8 |  |  | Y.53-02.X2 |  | Y.52-04.X7
[13 empty] | 2006-10-23 |  |  |  |  | Y.53-04.X7
[13 empty] | week9 |  |  |  |  | Y.52-02.X2
[13 empty] | 2006-10-23 |  |  |  |  | Y.51-02.X2
Y.53-02.X2

## PEOPLE
|  |  | Jan |  | Feb | March |  | April | May | Juin |  | July | Aug | Sept | Oct | Nov
Institution
Vlastik Kral |  | Prague
Tomas Slavicek |  | Prague
Petr Kubik |  | Prague
Alexandre Nadtochiy |  | Dubna
Scott Moncrieff |  | Melboune
Ashley French |  | Melboune
Jessica Metcalfe | GS | UC Santa Cruz
Ken Fowler | GS | UC Santa Cruz
Gabe Hare | GS | UC Santa Cruz
Yan Grange | GS | Nikhef
Kuo-Ming Lee |  | Academia Sinica
Edward Gornicki |  | Crakow
Jacek Pieron |  | Cracow
Barbara Toczek | GS | Cracow/Geneva
Stefan Koperny |  | Cracow
Regina Moles | GS | Valencia
Anthony Waugh | GS | Sydney
Andre Sopczak |  | Uppsala
Lars Lindquist |  | Uppsala
Staff |  | Geneva
Staff |  | Protvino
|  |  |  | 2 weeks |  |  | SCT contribution |  |  |  | Subsitence
[17 empty] | Vlastik Kral | x | Prague | 2006-03-01 | 2006-05-30
[17 empty] | Kuo-Ming Lee | x | Academia Sinica | 2006-05-08 | 2006-06-30
[17 empty] | Alexandre Nadtochiy | x | Dubna | 2006-04-17 |  |  |  | 2006-09-24
[17 empty] | Scott Moncrieff | x | Melboune | Feb | 2006-04-18 |  | 2006-06-12 | 2006-07-28
[17 empty] | Jessica Metcalfe | x | UC Santa Cruz | 2006-05-29 | 2006-06-12
[17 empty] | Ken Fowler | x | UC Santa Cruz | 2006-06-19 |  |  |  | 2006-08-14
[17 empty] | Tomas Slavicek | x | Prague | 2006-06-05 |  |  |  | 2006-09-01
[17 empty] | Petr Kubik | x | Prague | summer 2005 | 2006-06-05 |  | 2006-06-28
[17 empty] | Yan Grange | x | Nikhef | 2006-07-03
[17 empty] | Edward Gornicki | x | Crakow | 2006-07-03 |  |  |  | 9 months
[17 empty] | Alexandre Nadtochiy | \ | Dubna |  | 2006-10-27 | possibly extended
[17 empty] | Tomas Slavicek | \ | Prague |  | 2006-09-29
[17 empty] | Petr Kubik | \ | Prague |  | November
[17 empty] | Jacek Pieron | x | Cracow | 2006-08-20 | 2006-09-29 | returning 2nd week of October for 4 weeks
[17 empty] | Barbara Toczek | x | Cracow | 2006-07-24 | 2006-09-15
[17 empty] | Edward Gornicki | \ | Cracow |  | 2007-03-01 | 2007
[17 empty] | Regina Moles | x | Valencia | 2006-08-07 | 2006-09-29 | half day
[17 empty] | Andre Sopczak | x | Uppsala |  | 2006-12-01 | mornings | week of 18 Sep half week after 20 Sep
[17 empty] | Ken Fowler | \ | UC Santa Cruz |  | 2006-08-14
[17 empty] | Gabe Hare | x | UC Santa Cruz | 2006-08-04 | 2006-09-01
[17 empty] | Anthony Waugh | x | University of Sydney |  | 2006-08-11 | afternoons
[17 empty] | Stefan Koperny | x | Cracow | 2006-09-08 | 2006-09-29

## PP3
|  |  |  | to be installed |  | to be assembled
US side
Y.51-02.X2 | 0 | subracks installed | 8 | Subracks in pit next to rack
Y.52-02.X2 | 7 | subracks installed |  | Cables 2043715 and 2043716 swapped.
Y.53-02.X2 | 7 | subracks installed
Y.37-01.X6 | 7 | subracks installed
Y.47-01.X6 | 10 | subracks installed
Y.43-01.X6 | 10 | subracks installed
Y.52-01.X6 | 5 | subracks installed
Y.52-04.X7 | 11 | subracks installed
Y.53-04.X7 | 10 | subracks installed
USA side
Y.51-25.X1 | 11 | subracks installed |  | Cables 2048000 and 2047999 swapped.
Y.53-25.X2 | 10 | subracks installed
Y 52-25.X2 | 0 | subracks installed | 10 | subracks in pit next to rack
Y.53-26.X5 | 10 | subracks installed |  |  | 1 | mini subrack
Y.51-26.X5 | 10 | subracks installed |  |  | 1 | mini subrack
Y.51-23.X8 | 4 | subracks installed | 2 | subracks in pit next to rack |  |  | 1 | special subrack
Y.52-23.X8 | 0 | subracks installed | 6 | subracks in pit next to rack |  |  | 1 | special subrack
Y.53-23.X8 | 0 | subracks installed | 3 | subracks in pit next to rack | 4 | standard subracks | 1 | special subrack