## Plan
| 2005 |  | 2006 | [7 empty] | Comments
| Dec |  | Jan |  | Feb |  | March
Shifts*
Type II/III
QA | x | x |  | x | x | x | x | x |  |  | Pippa, Sandra, Pepe, Maarit & Martin
Production of double harness | x | x |  | x | x | [5 empty] | company
Delivery of Cable with PP3 connector |  | x |  | x | x | x | x | x |  |  | company
Installation | [10 empty] | TC team
Connection to PP3 |  | x |  | x | x | x | x | x |  |  | Sandra + team
Connection to DPP1 |  | x |  | x | x | x | x | x |  |  | Lars, Neil + experts
Test with DPP1 dummy load |  | 0.25 |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 70 | Sandra/Petr + SCT
Type IV
Delivery | x | x
installation US/USA | x | x |  | x | x | [5 empty] | TC team
Acceptance Test | 0.5 | 0.5 |  | 0.5 | [5 empty] | 60 | SCT Collaboration
After Installation Test | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 |  |  |  | 100 | SCT Collaboration
Connector Installation in situ | x | x |  | x | x | x |  |  |  |  | Company (QA:Petr/Sandra)
Final cable test |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 240 | SCT Collaboration
remaining shifts for type IV | [9 empty] | 400
PP3
Delivery | x | x |  | x | [6 empty] | Melbourne
Test | 0.25 | 0.25 |  | 0.25 | 0.25 |  |  |  |  | 40 | Shaun + SCT
Installation | x | x |  | x | x | [5 empty] | Ashley, Scott +
DCS cables
typeII | 0.5 | [8 empty] | 10 | Richard B. and team
type IV |  |  |  | 0.5 | [5 empty] | 10 | Richard B. and team
Heather cables | x | x |  | x | [6 empty] | Prague techs
remaining shifts | [9 empty] | 530
shift taken until Dec 1(mainly for type IV) | [9 empty] | 212
total number of shifts* | [9 empty] | 742
*shifts are 1 person/half day
2 persons/shift required

## withPP3
| 2005 |  |  |  | 2006 | [7 empty] | Comments
| Oct | Nov | Dec |  | Jan |  | Feb |  | March
Shifts*
Type II/III
QA |  |  | x | x |  | x | x | x | x | x |  |  | Pippa, Sandra, Pepe, Maarit & Martin
Production of double harness |  |  | x | x |  | x | x | [5 empty] | company
Delivery of Cable with PP3 connector |  |  |  | x |  | x | x | x | x | x |  |  | company
Installation | [12 empty] | TC team
Connection to PP3 | [5 empty] | x | x | x | x | x |  |  | Sandra + team
Connection to DPP1 | [5 empty] | x | x | x | x | x |  |  | Lars, Neil + experts
Test with DPP1 dummy load | [5 empty] | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 60 | Sandra/Petr + SCT
Type IV
Delivery |  |  | x | x
installation US/USA |  |  | x | x |  | x | x | [5 empty] | TC team
Acceptance Test & |  |  | 0.5 | 0.5 |  | 0.5 | [5 empty] | 60 | SCT Collaboration
After Installation Test && |  |  | 0.5 | 0.5 |  | 0.75 | 0.75 | 0.75 |  |  |  | 130 | SCT Collaboration
Connector Installation in situ |  |  | x | x |  | x | x | x | x |  |  |  | Company (QA:Petr/Sandra)
Final cable test | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 240 | SCT Collaboration
remaining shifts for type IV | [11 empty] | 430
PP3
Delivery |  |  | x | x |  | x | [6 empty] | Melbourne
Test** |  |  | 0.5 | 0.5 |  | 0.5 | 0.5 |  |  |  |  | 80 | Shaun + SCT
Installation*** |  |  | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 |  | 120 | Ashley, Scott + Vladimir + Edward
DCS cables
typeII |  |  | 0.5 | [8 empty] | 10 | Richard B. and team
type IV | [5 empty] | 0.5 | [5 empty] | 10 | Richard B. and team
Heather cables preparation |  |  | 1 | 1 |  | 1 | 1 | 1 | 1 |  |  | 240 | Steve +SCT
remaining shifts | [11 empty] | 950
shift taken until Dec 1(mainly for type IV) | [11 empty] | 212
total number of shifts* | [11 empty] | 1162
*shifts = 1 person/half day
2 persons/shift required
** Test of PP3 in the lab = 4200 units / [60/halfday to 96/halfday] x 1 shift x 2 people = {4000/[(60+96)/2]}*2 = 107
*** Installation of PP3 = 4200 units / [60 to 90/day] * 2 people * 2 shifts = 186 | [9 empty] | (not counted as shifts)
& acceptance test = 746 (as Dec 1) / 60/day * 2 shifts * 2 people = 50
&& after installation test = 2000 (USA15) / 60/day * 2 shifts * 2 people = 133